## Sheet1
Backlog Items | User Story | Task | Name | Status | Estimate | Priority
Sprint 1
Do the research about the project |  | Attend the first client meeting. | Nelson | Close | 10 | 1
|  | Group have second sprint meeting about the project. | All Members | Close | 10 | 2
Design the website |  | Design the login interface. | Eric | Close | 9 | 3
| 1,2,10,11,12,13 | Design the customer interface. | Nelson | Close | 9 | 3
| 3,4,5 | Design the staff interface. | Eric | Close | 9 | 3
| 6,7,8,9,14,15 | Design the manager interface. | Camille | Close | 9 | 3
|  | Design the homepage interface | Camille | Close | 9 | 3
Add rich CSS to previous web pages |  | Design the login interface. | Eric | Close | 8 | 4
|  | Design the homepage interface. | Camille | Close | 8 | 4
Backlog Items | User Story | Task | Name | Status | Estimate | Priority
Sprint 2
Database |  | Attend the second client meeting. | Camille | Close | 10 | 1
|  | Group have third sprint meeting about the project. | All Members | Close | 10 | 2
|  | Do the research about project database. | All Members | Close | 10 | 2
Design the database about the project |  | Create the ERD about project. | Camille | Close | 10 | 3
|  | Create the normalization. | Eric | Close | 9 | 3
|  | Create the login database. | Nelson | Close | 9 | 3
Design the database for customer | 1 | Create space rooms and book hotel room table. | Nelson | Close | 9 | 3
| 13 | Create hotel facilities table. | Nelson | Close | 9 | 3
| 2 | Create ordering food table. | Nelson | Close | 9 | 3
|  | Create meeting hall table. | Nelson | Close | 9 | 3
|  | Create cleaning the room table for customer. | Nelson | Close | 9 | 3
| 10 | Create view the reservations table for customer. | Nelson | Close | 9 | 3
Design the database for staff | 4 | Create clock in and clock out work table for staff. | Eric | Close | 9 | 3
| 3 | Create view staff work schedules table for staff. | Eric | Close | 9 | 3
| 5 | Create empty room table. | Eric | Close | 9 | 3
|  | Create full rooms table. | Eric | Close | 9 | 3
|  | Create when rooms are free table. | Eric | Close | 9 | 3
Design the database for manager | 6 | Create staff schedules table for manager. | Camille | Close | 9 | 3
| 7 | Create view staffs work time table for manager. | Camille | Close | 9 | 3
| 8 | Create register new staff table for manager. | Camille | Close | 9 | 3
| 14 | Create department information table for manager. | Camille | Close | 9 | 3
Backlog Items | User Story | Task | Name | Status | Estimate | Priority
Sprint 3
Test and complete the database about the project |  | Group have fourth sprint meeting about the project. | All Members | Close | 10 | 1
|  | Check and complete the ERD about project. | Camille | Close | 10 | 2
|  | Check and complete the normalization. | Eric | Close | 10 | 2
|  | Test and complete the login database. | Nelson | Close | 10 | 2
Test and complete the database for customer | 1 | Test and complete space rooms and book hotel room table. | Nelson | Close | 10 | 2
| 13 | Test and complete hotel facilities table. | Nelson | Close | 10 | 2
| 2 | Test and complete ordering food table. | Nelson | Close | 10 | 2
|  | Test and complete meeting hall table. | Nelson | Close | 10 | 2
|  | Test and complete cleaning the room table for customer. | Nelson | Close | 10 | 2
| 10 | Test and complete view the reservations table for customer. | Nelson | Close | 10 | 2
Test and complete the database for staff | 4 | Test and complete clock in and clock out work table for staff. | Eric | Close | 10 | 2
| 3 | Test and complete view staff work schedules table for staff. | Eric | Close | 10 | 2
| 5 | Test and complete empty room table. | Eric | Close | 10 | 2
|  | Test and complete full rooms table. | Eric | Close | 10 | 2
|  | Test and complete when rooms are free table. | Eric | Close | 10 | 2
Test and complete the database for manager | 6 | Test and complete staff schedules table for manager. | Camille | Close | 10 | 2
| 7 | Test and complete view staffs work time table for manager. | Camille | Close | 10 | 2
| 8 | Test and complete register new staff table for manager. | Camille | Close | 10 | 2
| 14 | Test and complete department information table for manager. | Camille | Close | 10 | 2